## Instructions
AI Audit Checklist
A comprehensive step-by-step checklist for auditing AI systems. Covers data quality, model validation, documentation, compliance, security, fairness, and performance.
How to use
• Work through each item top-to-bottom during an audit cycle
• Mark status as you complete each item
• Link evidence (documents, dashboards, reports) in the Evidence column
• Items marked N/A must include a justification
• All items must reach "Complete" or "N/A" before audit sign-off
Generated by VerifyWise — verifywise.ai

## Checklist
# | Category | Checklist item | Priority | Status | Evidence / Reference | Auditor | Completion date | Notes
1 | Data quality | Training data sources are documented with provenance and licensing information | Critical | Complete | Data catalog DC-v3.2, section 4 | M. Chen | 2025-01-10
2 | Data quality | Data quality metrics (completeness, accuracy, timeliness) are measured and tracked | High | Complete | DQ dashboard — link in Confluence | M. Chen | 2025-01-10 | Accuracy: 98.2%, Completeness: 99.1%
3 | Data quality | Sensitive/protected attributes in training data are identified and documented | Critical | Complete | Data sensitivity classification report | M. Chen | 2025-01-11
4 | Model validation | Model has been tested on an independent holdout dataset not used in training | Critical | Complete | Test report TR-2025-001 | J. Park | 2025-01-12 | F1: 0.94, AUC: 0.97
5 | Model validation | Performance has been evaluated across relevant demographic subgroups | High | In progress | Bias audit report (draft) | J. Park |  | Awaiting age group analysis
6 | Documentation | Model card is complete and up to date (purpose, limitations, metrics, data) | High | Complete | Model card MC-CS-v3.0 | L. Wei | 2025-01-13
7 | Compliance | DPIA has been conducted and approved by DPO | Critical | Complete | DPIA-2024-003 (signed) | A. Garcia | 2025-01-08
8 | Security | Adversarial robustness testing has been conducted | High | Not started |  |  |  | Scheduled for Feb sprint

## Dashboard
AI Audit Checklist — Dashboard
Total items
Complete
In progress
Not started
Completion rate
Overall audit progress
Completion |  |  | 75% | (6/8)
Status breakdown
Complete | 6
In progress | 1
Not started | 1
Progress by category
Data quality | 100% | (3/3)
Model validation | 50% | (1/2)
Documentation | 100% | (1/1)
Compliance | 100% | (1/1)
Security | 0% | (0/1)
Items by priority
Critical | 4
High | 4