## Instructions
AI Risk Assessment Matrix
Systematically identify, score, and mitigate risks across your AI portfolio. Aligned with NIST AI RMF and ISO 23894.
How to use
• Create one row per identified risk
• Score Likelihood (1-5) and Impact (1-5) — the Risk Score auto-calculates
• Assign a risk owner and define mitigation strategy
• Re-assess residual risk after mitigation is applied
• Use the Risk Heatmap sheet to visualize risk distribution
Scoring guide
• 1 = Very Low — Rare occurrence, negligible impact
• 2 = Low — Unlikely, minor impact
• 3 = Medium — Possible, moderate impact
• 4 = High — Likely, significant impact
• 5 = Critical — Almost certain, severe/catastrophic impact
Risk categories
• Performance: Accuracy, drift, latency, availability
• Fairness: Bias, discrimination, equity
• Security: Adversarial attacks, data leaks, prompt injection
• Privacy: GDPR violations, consent issues, re-identification
• Legal/Compliance: Regulatory non-compliance, liability
• Operational: Integration failures, skill gaps, vendor lock-in
• Reputational: Public trust, media exposure, brand damage
Generated by VerifyWise — verifywise.ai

## Risk Register
Risk ID | AI system / Model | Risk description | Risk category | Likelihood (1-5) | Impact (1-5) | Risk score | Risk rating | Mitigation strategy | Mitigation status | Residual risk | Risk owner | Date identified | Target resolution | Evidence / Reference
RSK-001 | Credit risk scoring model | Historical training data contains age-based bias leading to systematic discrimination against applicants under 25 | Fairness | 4 | 5 |  |  | Implement reweighting + adversarial debiasing; add fairness constraints to optimization | In progress | Medium | ML Ethics Lead | 2024-11-15 | 2025-03-01 | Bias audit report BA-2024-Q4
RSK-002 | Customer churn predictor | Model accuracy degrades over time as customer behavior patterns shift (concept drift) | Performance | 3 | 3 |  |  | Automated weekly drift detection using PSI + KS test; auto-alert when thresholds exceeded | Implemented | Low | MLOps Team | 2024-10-01 | 2025-01-15 | Monitoring dashboard MON-CHURN-01
RSK-003 | Support chatbot (LLM) | Prompt injection attacks could cause chatbot to leak internal knowledge base content or generate harmful responses | Security | 3 | 4 |  |  | Input sanitization layer + output guardrails + rate limiting; red team testing quarterly | In progress | Medium | Security Engineering | 2024-12-01 | 2025-02-28 | Red team report RT-2025-Q1
RSK-004 | Employee attrition predictor | Processing sensitive employee data without sufficient legal basis under GDPR Article 6; works council not consulted | Privacy | 2 | 5 |  |  | Conduct DPIA, obtain works council approval, implement data minimization and access controls | In progress | Low | DPO + HR Legal | 2024-09-20 | 2025-02-15 | DPIA-HR-2024-003
RSK-005 | Medical image triage | Misclassification of critical abnormalities could delay treatment — patient safety risk | Performance | 2 | 5 |  |  | Mandatory human review for all AI outputs; confidence threshold filtering; clinical validation study | Not started | Medium | Clinical AI Lead | 2025-01-05 | 2025-06-30 | Clinical protocol CP-2025-001
RSK-006 | All production models | No formal AI incident response procedure — ad-hoc handling increases response time and regulatory exposure | Operational | 4 | 3 |  |  | Develop AI incident response playbook; assign incident commander role; conduct tabletop exercise | In progress | Low | AI Governance Office | 2024-11-01 | 2025-03-15 | Governance roadmap GR-2025-Q1

## Risk Heatmap Guide
Risk Heatmap — Likelihood vs Impact
| Impact: 1 | Impact: 2 | Impact: 3 | Impact: 4 | Impact: 5
Likelihood: 5 | 5 - Medium | 10 - High | 15 - High | 20 - Critical | 25 - Critical
Likelihood: 4 | 4 - Medium | 8 - Medium | 12 - High | 16 - Critical | 20 - Critical
Likelihood: 3 | 3 - Low | 6 - Medium | 9 - High | 12 - High | 15 - High
Likelihood: 2 | 2 - Low | 4 - Medium | 6 - Medium | 8 - Medium | 10 - High
Likelihood: 1 | 1 - Low | 2 - Low | 3 - Low | 4 - Medium | 5 - Medium

## Dashboard
Risk Assessment — Dashboard
Total risks | Critical/High | Mitigated | Avg risk score
Risk rating distribution
Critical |  |  |  | 1
High |  |  |  | 3
Medium |  |  |  | 2
Low |  |  |  | 0
Risks by category
Fairness |  |  |  | 1
Performance |  |  |  | 2
Security |  |  |  | 1
Privacy |  |  |  | 1
Operational |  |  |  | 1
Mitigation progress
Implemented |  |  |  | 17% | (1/6)
In progress |  |  |  | 67% | (4/6)
Not started |  |  |  | 17% | (1/6)